## Start Here
Turnkey Water Bottling Plant Project Workbook
A practical buyer-side workbook for defining scope, assigning responsibilities, preparing the site, controlling acceptance and comparing quotations on one basis.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Project reference | Enter project name
Buyer / company | Enter legal or trading name
Destination | Country and installation city
Workbook owner | Name and role
Issue date | 2026-08-23 11:14
Current revision | Rev 0 — Working Draft
Recommended workflow
1 | Project Brief | Record known inputs, attach controlled evidence and keep unknowns visible.
2 | Responsibility Matrix | Assign each boundary before quotation comparison and mobilization.
3 | Site Readiness | Close factory, utilities, access, materials and safety prerequisites.
4 | FAT Checklist | Agree project-specific test conditions and evidence before the test.
5 | Installation | Control receiving, installation, commissioning, training and site actions.
6 | Handover | Collect the final technical dossier, software, records, spares and open items.
7 | Quote Comparison | Normalize three proposals by scope and evidence before scoring.
Live completion snapshot
Project brief | Responsibilities | Site readiness | FAT | Installation | Handover | Overall | Quote weights
0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
How to use this file: duplicate or version-control the workbook for each project. Keep blank or Open items visible; replace assumptions with approved evidence. Use the website project brief to send a structured enquiry after the buyer team has reviewed the workbook.
Reference: https://turnkeywaterbottlingplant.com/turnkey-water-bottling-plant-project-brief-template/

## Project Brief
Project Brief
Complete one controlled input set before requesting or comparing a turnkey water bottling plant proposal.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Responses entered | 31 | Open items | 31 | Inputs total | 31
Category | Required input | Buyer response | Units / options | Status | Owner / source | Notes / decision check
Commercial basis | Project / company name |  | Text | Open | Buyer | Use one controlled project reference
Commercial basis | Destination country and final installation city |  | Country / city | Open | Buyer | Drives standards, logistics and service planning
Product | Water category and intended label claim |  | Purified / drinking / spring / mineral / other | Open | Buyer + local adviser | Regulatory classification is jurisdiction-specific
Product | Raw-water source |  | Municipal / borehole / spring / surface / other | Open | Buyer | Attach current laboratory analysis
Product | Raw-water analysis date and report reference |  | Date / file name | Open | Buyer | Confirm sampling point and laboratory basis
Product | Finished-water specification |  | Project-specific | Open | Buyer + local adviser | State parameters and applicable market rules
Containers | Bottle formats |  | mL / L / gallon | Open | Buyer | List every launch and future format separately
Containers | Bottle material and neck finish |  | PET / HDPE / glass / other | Open | Buyer | Attach approved drawings or controlled samples
Containers | Preform or empty-bottle supply basis |  | Make / buy / mixed | Open | Buyer | Do not assume bottle making is included
Closures | Cap type and specification |  | Drawing / sample ref | Open | Buyer | Include closure material and tamper evidence
Labeling | Label type and artwork basis |  | BOPP / sleeve / self-adhesive / other | Open | Buyer | State barcode, code and inspection requirements
Packing | Secondary pack configuration |  | Shrink / carton / tray / other | Open | Buyer | List bottles per pack and pallet pattern
Capacity | Saleable output target by format |  | Bottles per hour | Open | Buyer | State whether output is nominal or accepted saleable output
Capacity | Operating calendar |  | Hours / shifts / days | Open | Buyer | Include cleaning, changeover and planned downtime
Capacity | Format mix and changeover frequency |  | % / schedule | Open | Buyer | Use expected commercial mix, not only maximum speed
Factory | Available building footprint and clear height |  | m × m × m | Open | Buyer | Attach dimensioned layout and column grid
Factory | Floor, drainage and hygiene zoning basis |  | Description / drawing | Open | Buyer + local contractor | Identify finished and unfinished civil work
Utilities | Incoming electrical supply |  | V / Hz / phase / capacity | Open | Buyer + local contractor | Include allowable fluctuation and earthing basis
Utilities | Water, air, steam, cooling and drainage availability |  | Flow / pressure / quality | Open | Buyer + local contractor | Define each battery limit and connection point
Utilities | Environmental design conditions |  | Temperature / humidity / altitude | Open | Buyer | Include dust, corrosion or climate constraints
Scope | Requested process and equipment boundary |  | Included / excluded list | Open | Buyer | Map from source-water inlet to pallet or warehouse
Scope | Automation, controls and data interface |  | PLC / SCADA / ERP / reporting | Open | Buyer + IT | Define cybersecurity and remote-access rules
Scope | Laboratory, QA and inspection equipment |  | Included / buyer-supplied | Open | Buyer | Link equipment to the agreed control plan
Services | Installation, commissioning and training boundary |  | Responsibility split | Open | Buyer | Define travel, visas, labor, lifting and tools
Acceptance | FAT objectives and witness plan |  | Tests / samples / duration | Open | Buyer + supplier | Use measurable project-specific evidence
Acceptance | Site acceptance and handover basis |  | Tests / documents / sign-off | Open | Buyer + supplier | Separate completion, acceptance and production ramp-up
Documents | Required drawings, manuals and language |  | Format / language / timing | Open | Buyer | Include revision, approval and as-built requirements
Schedule | Target commercial production window |  | Date / priority | Open | Buyer | Final schedule follows approved inputs and signed scope
Logistics | Trade term, unloading and site access basis |  | Incoterm / port / route | Open | Buyer | Confirm container, crane and access constraints
Compliance | Applicable local legal and certification requirements |  | Authority / standard | Open | Buyer + local adviser | Buyer must validate legal applicability
Open items | Known unknowns requiring clarification |  | Issue list | Open | All parties | Keep assumptions visible until formally closed

## Responsibility Matrix
Responsibility Matrix
Use this as a discussion matrix. Replace Assign / Confirm labels with named contractual responsibility before release.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Open items | 20 | Work packages | 20
Work package | Boundary / deliverable | Buyer | Supplier / integrator | Local contractor | Evidence / decision record | Status | Notes
Project inputs | Issue controlled project brief and approved changes | Assign | Assign | Confirm | Versioned brief / change log | Open | Name one owner for each revision
Regulatory | Confirm permits, product classification and local compliance path | Assign | Confirm support | Assign | Written local advice / permit plan | Open | Do not infer jurisdiction-specific approval
Water basis | Provide representative raw-water analysis | Assign | Review | Confirm sampling | Laboratory report and sample record | Open | Analysis age and sampling point controlled
Bottle package | Approve bottle, preform, cap, label and pack specifications | Assign | Review interface | Confirm suppliers | Approved drawings / samples | Open | Revision-controlled references
Process design | Develop treatment and hygienic process basis | Review | Assign | Support | PFD / design basis / equipment list | Open | Performance basis project-specific
Layout | Coordinate equipment layout, access and maintenance clearances | Approve | Assign | Review civil fit | Approved general arrangement | Open | Include operator and material flows
Civil works | Design and execute building, foundations, floors and drainage | Approve | Provide loads/interfaces | Assign | Civil drawings / completion record | Open | Responsibility depends on signed scope
Power | Provide site electrical infrastructure to agreed battery limits | Approve | Provide load list | Assign | Single-line / test records | Open | Confirm voltage, frequency and earthing
Utilities | Provide water, air, steam, cooling and drainage connections | Approve | Provide consumption/interface data | Assign | Utility matrix / test records | Open | Define quality, flow and pressure
Automation | Define controls, data and remote-access boundary | Approve | Assign within scope | Support IT/site | I/O list / architecture / access rule | Open | Include cybersecurity approval
Safety | Complete local machine and site safety assessment | Assign | Provide equipment information | Assign | Risk record / action closure | Open | Local legal review remains buyer-owned unless agreed
Manufacture | Build and internally test equipment within approved scope | Witness as agreed | Assign | Support | Inspection records / manufacturing status | Open | Selected manufacturing resources documented
FAT | Agree protocol, samples, witnesses and action closure | Approve / witness | Prepare / execute | Support | Signed FAT protocol and punch list | Open | No generic pass/fail assumption
Logistics | Packing, shipment, customs, unloading and storage boundary | Assign by Incoterm | Assign by Incoterm | Support site handling | Packing list / receipt inspection | Open | Name risk transfer and handoff points
Installation | Labor, supervision, tools, lifting and consumables | Assign | Assign | Assign | Mobilization plan / daily records | Open | Split must match quotation and contract
Commissioning | Utilities, production materials, trials and support team | Assign | Assign | Support | Commissioning plan / issue log | Open | State who provides water, preforms, caps and film
Training | Trainees, language, modules and competence evidence | Assign attendees | Assign delivery | Support | Attendance / module records | Open | Separate orientation from competence validation
Acceptance | Site test, open-item closure and sign-off process | Approve / witness | Execute / evidence | Support | Signed SAT / acceptance record | Open | Use signed measurable criteria
Documentation | Manuals, drawings, certificates and as-built package | Approve requirements | Compile within scope | Support local documents | Document register / transmittal | Open | Agree language and delivery milestones
Handover | Transfer operating records, spares and unresolved items | Accept | Provide | Support | Handover dossier / residual action list | Open | Define post-handover support contact

## Site Readiness
Site Readiness Checklist
Close prerequisites before equipment mobilization. Record actual evidence at the agreed battery limits.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Open items | 22 | Checkpoints | 22
Category | Readiness checkpoint | Required evidence | Owner | Target date | Status | Gap / corrective action | Notes / reference
Project control | Latest approved layout and equipment boundary available | Approved revision and distribution list | Buyer |  | Open
Access | Container, truck and crane access route verified | Route survey, turning radius and lifting zone | Buyer / contractor |  | Open
Building | Room dimensions, clear heights and columns checked | As-built dimensions against layout | Buyer / contractor |  | Open
Floor | Floor completion, flatness and load capacity confirmed | Inspection report and equipment loads | Buyer / contractor |  | Open
Drainage | Drain locations, capacity, traps and hygienic falls ready | Drainage drawing and flow test | Buyer / contractor |  | Open
Hygiene | Zoning and personnel/material flows implemented | Approved hygiene flow and barriers | Buyer |  | Open
Electrical | Incoming power, panels, protection and earthing ready | Electrical test certificates | Buyer / contractor |  | Open
Compressed air | Pressure, flow, quality and connection points ready | Measured test at battery limit | Buyer / contractor |  | Open
Process water | Water supply, storage and connection points ready | Measured flow/pressure and quality | Buyer / contractor |  | Open
Cooling | Cooling-water or refrigeration interface ready if required | Capacity and temperature test | Buyer / contractor |  | Open
Steam / heat | Steam or thermal source ready if required | Pressure, quality and safety inspection | Buyer / contractor |  | Open
Waste | Wastewater and solid-waste routes available | Discharge approval and connection test | Buyer |  | Open
Network | Controls network and approved remote-access path ready | IT approval and connection test | Buyer / IT |  | Open
Lighting | Safe task lighting and emergency lighting operational | Site inspection | Buyer / contractor |  | Open
Ventilation | Temperature, humidity and ventilation within design basis | Environmental measurements | Buyer / contractor |  | Open
Storage | Dry, secure storage for equipment, parts and materials | Receiving and preservation plan | Buyer |  | Open
Lifting | Certified lifting equipment and operators available | Certificates and lift plan | Buyer / contractor |  | Open
Safety | Site induction, permits, PPE and emergency controls active | Approved HSE plan | Buyer / contractor |  | Open
Labor | Agreed local labor and trades mobilized | Roster and competence evidence | Buyer / contractor |  | Open
Materials | Approved bottles/preforms, caps, labels and packs available | Quantity and incoming inspection | Buyer |  | Open
Laboratory | Required QC instruments, methods and staff available | Calibration and method records | Buyer |  | Open
Readiness gate | Joint site-readiness review completed before mobilization | Signed readiness record and action list | Buyer + supplier |  | Open

## FAT Checklist
Factory Acceptance Test Checklist
Build the signed FAT protocol before the test. This checklist does not create universal acceptance criteria.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Open results | 21 | Checks | 21
Test area | Verification | Method / evidence | Acceptance basis | Responsible | Witness | Result | Open action / reference
Protocol | Approved FAT protocol and test sequence | Controlled signed document | Project-specific protocol | Supplier / integrator | Buyer / agreed witness | Open
Traceability | Equipment identification matches approved scope | Nameplates, list and drawings | Approved equipment list | Supplier / integrator | Buyer / agreed witness | Open
Documentation | Latest drawings, manuals and software list available | Document register review | Agreed FAT document list | Supplier / integrator | Buyer / agreed witness | Open
Safety | Guards, interlocks and emergency stops demonstrated | Functional checks and risk actions | Approved safety basis | Supplier / integrator | Buyer / agreed witness | Open
Controls | PLC/HMI sequences and alarms demonstrated | I/O and functional test | Approved functional description | Supplier / integrator | Buyer / agreed witness | Open
Recipes | Format recipes and protected parameters checked | Recipe review and change test | Approved format list | Supplier / integrator | Buyer / agreed witness | Open
Interfaces | Upstream/downstream interlocks simulated or tested | Signal matrix / simulation record | Approved interface matrix | Supplier / integrator | Buyer / agreed witness | Open
Water treatment | Specified process sequence and instrument functions checked | Functional run / instrument record | Approved design basis | Supplier / integrator | Buyer / agreed witness | Open
Bottle handling | Container transfer and accumulation behavior checked | Run with approved test containers | Agreed test conditions | Supplier / integrator | Buyer / agreed witness | Open
Rinse/fill/cap | Sequence, settings, hygiene controls and rejection checked | Controlled trial and observations | Agreed product/test medium basis | Supplier / integrator | Buyer / agreed witness | Open
Closure | Cap feed, application and verification checked | Approved caps and measurement method | Project-specific closure criteria | Supplier / integrator | Buyer / agreed witness | Open
Labeling | Label application and code interfaces checked | Approved labels/artwork trial | Project-specific visual criteria | Supplier / integrator | Buyer / agreed witness | Open
Packing | Pack formation and transfer checked | Approved film/carton/tray trial | Approved pack specification | Supplier / integrator | Buyer / agreed witness | Open
Changeover | Defined format change tasks demonstrated | Timed controlled demonstration | Agreed tasks and starting condition | Supplier / integrator | Buyer / agreed witness | Open
Performance | Trial duration, inputs and output evidence captured | Counter logs, rejects and downtime | Signed project-specific test basis | Supplier / integrator | Buyer / agreed witness | Open
Utilities | Observed utility conditions recorded during test | Meter readings / temporary basis | Agreed FAT limitations | Supplier / integrator | Buyer / agreed witness | Open
Quality | Sample inspection and measurement records complete | Approved methods and calibrated tools | Project-specific sample plan | Supplier / integrator | Buyer / agreed witness | Open
Spares | Commissioning spares, tools and change parts identified | Inventory check | Approved supply list | Supplier / integrator | Buyer / agreed witness | Open
Cybersecurity | Accounts, backups and remote-access rules reviewed | Access list and backup evidence | Buyer-approved policy | Supplier / integrator | Buyer / IT | Open
Punch list | Every deviation has owner, due date and disposition | Controlled open-action log | Agreed closure classification | Supplier / integrator | Buyer / agreed witness | Open
Release | Packing/release decision records residual conditions | Signed FAT summary | Contract and approved protocol | Buyer + supplier | Authorized signatories | Open

## Installation
Installation & Commissioning Tracker
Coordinate tasks and evidence from mobilization through site testing and handover.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Open tasks | 20 | Tasks | 20
Phase | Task | Prerequisite | Owner | Planned date | Actual date | Status | Evidence / action
Mobilization | Confirm site-readiness gate and open actions | Signed readiness review | Buyer + supplier |  |  | Open
Mobilization | Approve HSE, permits and daily coordination method | Site safety induction | Buyer / contractor |  |  | Open
Receiving | Inspect shipment condition and packing-list quantities | Safe unloading area | Buyer + supplier |  |  | Open
Receiving | Record damage, shortages and preservation needs | Inspection photos and issue log | Buyer + supplier |  |  | Open
Positioning | Verify equipment centerlines, levels and clearances | Approved layout and benchmarks | Installer / supervisor |  |  | Open
Mechanical | Assemble equipment and conveyors to approved layout | Positioned equipment | Installer / supervisor |  |  | Open
Mechanical | Complete piping, drains and hygienic connections | Approved P&ID / interfaces | Installer / contractor |  |  | Open
Electrical | Complete power, controls and earthing connections | Approved drawings and safe isolation | Electrician / supervisor |  |  | Open
Utilities | Connect and label every battery-limit utility | Utilities proven ready | Contractor / supervisor |  |  | Open
Inspection | Check guarding, access, fasteners and workmanship | Mechanical completion checklist | Buyer + supplier |  |  | Open
Pre-commissioning | Clean, flush, lubricate and verify rotation | Mechanical completion | Supplier / installer |  |  | Open
Pre-commissioning | Verify instruments, I/O and emergency circuits | Electrical completion | Supplier / electrician |  |  | Open
Dry run | Run sections without product under controlled conditions | Pre-commissioning release | Supplier + buyer |  |  | Open
Wet run | Introduce water and confirm hygienic process sequence | Water and drainage available | Supplier + buyer |  |  | Open
Materials | Approve trial bottles/preforms, caps, labels and packs | Incoming QC complete | Buyer |  |  | Open
Commissioning | Tune interfaces and record controlled changes | Approved change-control method | Supplier + buyer |  |  | Open
Training | Deliver operator, maintenance and sanitation modules | Named trainees and language agreed | Supplier + buyer |  |  | Open
Site test | Execute agreed site acceptance or performance test | Stable utilities and materials | Buyer + supplier |  |  | Open
Actions | Classify and close safety, function and documentation actions | Controlled punch list | Assigned owners |  |  | Open
Handover | Transfer records, backups, spares and support contacts | Handover checklist | Buyer + supplier |  |  | Open

## Handover
Handover Dossier Checklist
Verify deliverables, approvals and residual actions before the project handover record is signed.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Completion | 0% | Open items | 20 | Deliverables | 20
Deliverable | Expected evidence | Provided by | Verified by | Status | Document reference | Comments / residual action
Approved equipment list | Final supplied scope with serial / identification references | Supplier / integrator | Buyer | Open
As-built layout | Final arrangement including approved field changes | Supplier / integrator | Buyer | Open
P&ID / process drawings | Final process and utility connections | Supplier / integrator | Buyer | Open
Electrical drawings | Final power, control and panel documents | Supplier / integrator | Buyer | Open
PLC/HMI backup | Controlled software backup and version record | Supplier / integrator | Buyer / IT | Open
User access record | Accounts, roles and remote-access disposition | Supplier / integrator | Buyer / IT | Open
Operating manuals | Operation, setup, sanitation and safety instructions | Supplier / integrator | Buyer | Open
Maintenance manuals | Preventive tasks, lubrication and troubleshooting | Supplier / integrator | Buyer | Open
Parts lists | Wear, recommended and commissioning spares identified | Supplier / integrator | Buyer | Open
Certificates / records | Agreed inspection, material, calibration or test documents | Supplier / integrator | Buyer | Open
FAT record | Signed protocol, evidence and residual action disposition | Supplier / integrator | Buyer | Open
Installation record | Completion checks and approved field changes | Installer / supervisor | Buyer | Open
Commissioning record | Settings, trial conditions, issues and resolutions | Supplier / integrator | Buyer | Open
Site acceptance record | Signed project-specific test and result | Buyer + supplier | Authorized signatories | Open
Training record | Modules, attendees and delivered language/materials | Supplier + buyer | Buyer | Open
Open-item register | Owner, due date, risk and closure evidence | Buyer + supplier | Project manager | Open
Warranty / support basis | Signed start point, exclusions and contact route | Supplier / integrator | Buyer | Open
Consumables / tools | Delivered quantities and storage instructions | Supplier / integrator | Buyer | Open
Production responsibility | Post-handover operating, QC and maintenance owners named | Buyer | Project sponsor | Open
Final handover | Authorized acceptance of dossier and residual actions | Buyer + supplier | Authorized signatories | Open

## Quote Comparison
Turnkey Quotation Comparison
Normalize three proposals against one controlled brief. Scores support discussion; they do not replace technical or commercial due diligence.
Project-specific planning aid — not a fixed equipment package, performance guarantee, price, schedule or contract. Confirm every final requirement in signed project documents.
Weight total | 100% | Supplier A weighted | 0 | Supplier B weighted | 0 | Supplier C weighted | 0 |  | Scoring guide: 1 = unsupported / material gap; 3 = acceptable with clarification; 5 = strong, comparable evidence. Leave blank until reviewed.
Category | Criterion | Weight | Supplier A response / evidence | A score | Supplier B response / evidence | B score | Supplier C response / evidence | C score | Comparison notes | Required clarification | Status
Scope | Boundary completeness from water source to agreed handoff | 10% | [8 empty] | Open
Inputs | Documented assumptions and exclusions | 6% | [8 empty] | Open
Water process | Treatment basis tied to raw/finished-water evidence | 8% | [8 empty] | Open
Containers | Confirmed bottle, cap, label and pack compatibility | 7% | [8 empty] | Open
Capacity | Comparable output definition and test conditions | 8% | [8 empty] | Open
Utilities | Consumption and battery-limit definition | 5% | [8 empty] | Open
Layout | Factory fit, access, hygiene and maintainability review | 6% | [8 empty] | Open
Controls | Automation, interfaces, data and access boundary | 5% | [8 empty] | Open
Safety/compliance | Declared basis and buyer-side local validation needs | 5% | [8 empty] | Open
FAT | Measurable FAT protocol, materials and evidence | 7% | [8 empty] | Open
Site services | Installation, commissioning and training split | 7% | [8 empty] | Open
Documentation | Language, timing, revision and as-built deliverables | 5% | [8 empty] | Open
Schedule | Milestones, dependencies and change-control basis | 5% | [8 empty] | Open
Project management | Interface ownership, reporting and change-control evidence | 5% | [8 empty] | Open
Commercial | Price basis, Incoterm, taxes, validity and payment structure | 5% | [8 empty] | Open
Lifecycle | Spares, service route and documented support scope | 6% | [8 empty] | Open